## 00_Dashboard
NSIGHT / PDMG Architecture Registry A~J — FINAL V6
Registry | Count | Status / Meaning | Severity | Count
A ServiceId | 13 | Current Handler Registry | Critical | 14
B Application Code | 50 | 6 Groups / 50 Apps | High | 70
C Package/Class | 32 | Evidence-supported index | Medium | 9
D Mapper | 4 | Confirmed Mapper XML | Medium/High | 6
D Representative SqlId | 6 | Representative naming
E HW Inventory | 12 | Baseline/Candidate/Open
E SW Inventory | 23 | AS-IS/Baseline/GAP
F Interface | 11 | Current + Target/Open
G Configuration | 18 | Current Snapshot / GAP
H ADR | 40 | 40 Decision Tasks
I GAP | 99 | Cross-domain GAP registry
J Evidence | 25 | Evidence Master

## A_ServiceId
A ServiceId Registry
ServiceId | Program | Type | Meaning | Seq | Handler | Status | Evidence
mgcoa5530S0 | mgcoa5530 | S | 조회 | 0 | mgcoa5530Handler | [AS-IS] | Current Handler Registry
mgcoa8888S0 | mgcoa8888 | S | 조회 | 0 | mgcoa8888Handler | [AS-IS] | Current Handler Registry
mgcoa8888D0 | mgcoa8888 | D | 삭제 | 0 | mgcoa8888Handler | [AS-IS] | Current Handler Registry
mgcoa9000S0 | mgcoa9000 | S | 조회 | 0 | mgcoa9000Handler | [AS-IS] | Current Handler Registry
mgcoa9000C0 | mgcoa9000 | C | 등록 | 0 | mgcoa9000Handler | [AS-IS] | Current Handler Registry
mgcoa9000U0 | mgcoa9000 | U | 수정 | 0 | mgcoa9000Handler | [AS-IS] | Current Handler Registry
mgcoa9000D0 | mgcoa9000 | D | 삭제 | 0 | mgcoa9000Handler | [AS-IS] | Current Handler Registry
mgcoa9001S0 | mgcoa9001 | S | 조회 | 0 | mgcoa9001Handler | [AS-IS] | Current Handler Registry
mgcoa9001C0 | mgcoa9001 | C | 등록 | 0 | mgcoa9001Handler | [AS-IS] | Current Handler Registry
mgcoa9001U0 | mgcoa9001 | U | 수정 | 0 | mgcoa9001Handler | [AS-IS] | Current Handler Registry
mgcoa9001D0 | mgcoa9001 | D | 삭제 | 0 | mgcoa9001Handler | [AS-IS] | Current Handler Registry
mgcoa9100S0 | mgcoa9100 | S | 조회 | 0 | mgcoa9100Handler | [AS-IS] | Current Handler Registry
mgcoa9999S0 | mgcoa9999 | S | 조회 | 0 | mgcoa9999Handler | [AS-IS] | Current Handler Registry

## B_AppCode
B AppCode Registry
Group | Group Name | App | Canonical Key | Korean | English | Status | Evidence
MP | 마케팅플랫폼 | CO | MP-CO | 공통 | Common | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | IC | MP-IC | 통합고객 | Integration Customer | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | PC | MP-PC | 개인고객 | Private Customer | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | BC | MP-BC | 기업고객 | Business Customer | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | MS | MP-MS | 미니 싱글뷰 | Mini SingleView | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | SA | MP-SA | 상담판매 | Sale | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | PD | MP-PD | 통합상품 | Product | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | CM | MP-CM | 캠페인 | Campaign | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | EB | MP-EB | EBM | EBM | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | EP | MP-EP | 실시간 처리 | Event Processing | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | BP | MP-BP | 행동정보 처리 | Behavior Information Processing | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | BD | MP-BD | 고객 행동 데이터 | Customer Behavior Data | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | SS | MP-SS | 영업지원 | Sales Support | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | CS | MP-CS | CS | Customer Service | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | CT | MP-CT | 컨텐츠 | Contents | [BASELINE] | Application Code Definition
MP | 마케팅플랫폼 | MG | MP-MG | 메시지 | Message | [BASELINE] | Application Code Definition
RD | 데이터플랫폼 RDW | CO | RD-CO | 공통 | Common | [BASELINE] | Application Code Definition
RD | 데이터플랫폼 RDW | SR | RD-SR | 실시간 SoR | Source of Record | [BASELINE] | Application Code Definition
RD | 데이터플랫폼 RDW | ZD | RD-ZD | 준실시간요약집계 | Zipped Data | [BASELINE] | Application Code Definition
RD | 데이터플랫폼 RDW | RM | RD-RM | 준실시간보고서마트 | Report Data Mart | [BASELINE] | Application Code Definition
RD | 데이터플랫폼 RDW | FA | RD-FA | 피드백 | Feedback Area | [BASELINE] | Application Code Definition
AD | 데이터플랫폼 ADW | CO | AD-CO | 공통 | Common | [BASELINE] | Application Code Definition
AD | 데이터플랫폼 ADW | SR | AD-SR | 분석 SoR | Source of Record | [BASELINE] | Application Code Definition
AD | 데이터플랫폼 ADW | ZD | AD-ZD | 분석통합요약집계 | Zipped Data Area | [BASELINE] | Application Code Definition
AD | 데이터플랫폼 ADW | UM | AD-UM | 분석단위업무마트 | Unit-business Mart | [BASELINE] | Application Code Definition
AD | 데이터플랫폼 ADW | RM | AD-RM | 분석보고서마트 | Report Data Mart | [BASELINE] | Application Code Definition
AD | 데이터플랫폼 ADW | FA | AD-FA | 피드백 | Feedback Area | [BASELINE] | Application Code Definition
AD | 데이터플랫폼 ADW | DA | AD-DA | 분석지원 | DW Analysis Assistance | [BASELINE] | Application Code Definition
BI | BI 포탈 | PT | BI-PT | BI 포탈 | Portal | [BASELINE] | Application Code Definition
BI | BI 포탈 | CR | BI-CR | 신용실적 | Credit Result | [BASELINE] | Application Code Definition
BI | BI 포탈 | OA | BI-OA | OLAP | Online Analysis Process | [BASELINE] | Application Code Definition
BI | BI 포탈 | SB | BI-SB | Self BI | Self Business Intelligence | [BASELINE] | Application Code Definition
BI | BI 포탈 | UI | BI-UI | 신 BI 포털 UI/UX | UI/UX | [BASELINE] | Application Code Definition
DG | 데이터거버넌스 | CO | DG-CO | 공통 | Common | [BASELINE] | Application Code Definition
DG | 데이터거버넌스 | BM | DG-BM | 비즈메타 | Biz-Meta System | [BASELINE] | Application Code Definition
DG | 데이터거버넌스 | DQ | DG-DQ | 데이터품질 | Data Quality | [BASELINE] | Application Code Definition
DG | 데이터거버넌스 | DL | DG-DL | 데이터흐름 | Data Lineage | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | AM | IM-AM | 아키텍처 관리 | Architecture Management | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | SC | IM-SC | 시스템 공통 | System Common | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | DP | IM-DP | 배포 | Deployment | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | FW | IM-FW | 프레임워크 | Framework | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | LB | IM-LB | 라이브러리 | Library | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | SM | IM-SM | 소스 코드 버전 관리 | Source Code Version Management | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | XM | IM-XM | 정보단말 관리 | UI/UX Management | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | XD | IM-XD | 정보단말 배포 | UI/UX Deployment | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | BJ | IM-BJ | 배치작업 처리 | Batch Job Processing | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | CD | IM-CD | 실시간 중계 | CDC Gateway | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | DT | IM-DT | 데이터 치환 적재 | Data Transform Load | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | RD | IM-RD | 보고서 디자이너 | Report Designer | [BASELINE] | Application Code Definition
IM | IT서비스 및 업무지원 | IG | IM-IG | 거래 공통 메모리 | In Memory Data Grid | [BASELINE] | Application Code Definition

## C_PackageClass
C PackageClass Registry
Module | Type | Package | Class/Stem | Role | Status
pdmg-service | Root Package | nhnis.mg.co.a.* |  | Business Application | [AS-IS]
pdmg-service | Handler Package | nhnis.mg.co.a.entry.handler |  | TCF ON Adapter | [AS-IS]
pdmg-service | Controller Package | nhnis.mg.co.a.application.controller |  | TCF OFF / MVC Adapter | [AS-IS]
pdmg-service | Facade Package | nhnis.mg.co.a.application.facade |  | Business Use Case Boundary | [AS-IS]
pdmg-service | Service Package | nhnis.mg.co.a.application.service |  | Business Logic | [AS-IS]
pdmg-service | DTO Package | nhnis.mg.co.a.application.dto |  | Input/Output DTO | [AS-IS]
pdmg-service | DAO Package | nhnis.mg.co.a.persistence.dao |  | Persistence Boundary | [AS-IS]
pdmg-fw | Framework Root | nhnis.fw.* |  | Framework Runtime | [AS-IS]
pdmg-fw | Framework Root | com.ims.superspring.* |  | Framework Runtime | [AS-IS]
pdmg-ui | UI Root | nhnis.mg.ui.* |  | UI/Presentation | [AS-IS]
pdmg-jwt | JWT Root | nhnis.mg.jw.a.* |  | Authentication/Token | [AS-IS]
Mapper | Resource Root | rdw.mg.co.a/ |  | MyBatis Mapper Resource | [AS-IS]
pdmg-service | Class | nhnis.mg.co.a.entry.handler | mgcoa9000Handler.java | Handler | [CONFIRMED]
pdmg-service | Class | nhnis.mg.co.a.application.controller | mgcoa9000Controller.java | Controller | [CONFIRMED]
pdmg-service | Class | nhnis.mg.co.a.application.facade | mgcoa9000Facade.java | Facade | [CONFIRMED]
pdmg-service | Class | nhnis.mg.co.a.application.service | mgcoa9000Service.java | Service | [CONFIRMED]
pdmg-service | Class | nhnis.mg.co.a.persistence.dao | mgcoa9000DAO.java | DAO | [CONFIRMED]
pdmg-service | DTO | nhnis.mg.co.a.application.dto | mgcoa9000S0DTOin.java | S0 Input | [CONFIRMED]
pdmg-service | DTO | nhnis.mg.co.a.application.dto | mgcoa9000S0DTOout.java | S0 Output | [CONFIRMED]
pdmg-service | DTO | nhnis.mg.co.a.application.dto | mgcoa9000C0DTOin.java | C0 Input | [CONFIRMED]
pdmg-service | DTO | nhnis.mg.co.a.application.dto | mgcoa9000U0DTOin.java | U0 Input | [CONFIRMED]
pdmg-service | DTO | nhnis.mg.co.a.application.dto | mgcoa9000D0DTOin.java | D0 Input | [CONFIRMED]
pdmg-service | Class Stem | nhnis.mg.co.a.entry.handler | mgcoa9001Handler | Handler | [CONFIRMED]
pdmg-service | Class Stem | nhnis.mg.co.a.application.controller | mgcoa9001Controller | Controller | [CONFIRMED]
pdmg-service | Class Stem | nhnis.mg.co.a.application.facade | mgcoa9001Facade | Facade | [CONFIRMED]
pdmg-service | Class Stem | nhnis.mg.co.a.application.service | mgcoa9001Service | Service | [CONFIRMED]
pdmg-service | Class Stem | nhnis.mg.co.a.persistence.dao | mgcoa9001DAO | DAO | [CONFIRMED]
pdmg-service | DAO FQCN | nhnis.mg.co.a.persistence.dao | mgcoa8888DAO | Mapper Namespace Exact Match Reference | [CONFIRMED]
pdmg-service | Handler Stem | nhnis.mg.co.a.entry.handler | mgcoa5530Handler | Handler Registry | [CONFIRMED]
pdmg-service | Handler Stem | nhnis.mg.co.a.entry.handler | mgcoa8888Handler | Handler Registry | [CONFIRMED]
pdmg-service | Handler Stem | nhnis.mg.co.a.entry.handler | mgcoa9100Handler | Handler Registry | [CONFIRMED]
pdmg-service | Handler Stem | nhnis.mg.co.a.entry.handler | mgcoa9999Handler | Handler Registry | [CONFIRMED]

## D_Mapper
D Mapper Registry
Resource Path | Mapper XML | Status | DAO/Namespace | Table/View | Note
rdw.mg.co.a/ | mgcoa5530-ORA.xml | [CONFIRMED] | [OPEN] | [OPEN] | SqlId/Table 전수 Source Scan 필요
rdw.mg.co.a/ | mgcoa8888-ORA.xml | [CONFIRMED] | nhnis.mg.co.a.persistence.dao.mgcoa8888DAO | [OPEN] | Namespace Exact Match 확인
rdw.mg.co.a/ | mgcoa9000-ORA.xml | [CONFIRMED] | nhnis.mg.co.a.persistence.dao.mgcoa9000DAO | [OPEN] | Java DAO↔Mapper 연결 확인
rdw.mg.co.a/ | mgcoa9001-ORA.xml | [CONFIRMED] | nhnis.mg.co.a.persistence.dao.mgcoa9001DAO | [OPEN] | Mapper class stem 확인

## D_SqlId
D SqlId Registry
SqlId | Program | Tx | Role | Status | Table/View
mgcoa9000S0_S0 | mgcoa9000 | S0 | Representative | [CONFIRMED NAMING] | Table/View [OPEN]
mgcoa9000S0_COUNT | mgcoa9000 | S0 | Count helper | [CONFIRMED NAMING] | Table/View [OPEN]
mgcoa9000C0_C0 | mgcoa9000 | C0 | Create | [CONFIRMED NAMING] | Table/View [OPEN]
mgcoa9000U0_U0 | mgcoa9000 | U0 | Update | [CONFIRMED NAMING] | Table/View [OPEN]
mgcoa9000D0_D0 | mgcoa9000 | D0 | Delete | [CONFIRMED NAMING] | Table/View [OPEN]
..._exists | Generic | helper | Existence helper | [SOURCE MAY EXIST] | Do not constrain to CRUD suffix only

## E_Physical
E Physical Registry
No | 영역 | HW Role | 자원유형 | 센터 | 환경 | 논리노드 | CPU | Memory | Storage | NIC/Network | HA 구성 | DR Pair | 상태 | 비고
1 | Traffic | GSLB | Network Appliance/Service | MAIN/DR | PROD | Global Traffic | [OPEN] | [OPEN] | N/A | External/Center | HA 정책 [OPEN] | DR Site | [BASELINE] | DNS/Health/TTL 상세 미확정
2 | Traffic | L4 | Load Balancer | MAIN/DR | PROD | Load Balancing | [OPEN] | [OPEN] | N/A | WEB/WAS Network | Pair/N+1 [OPEN] | DR L4 | [BASELINE] | VIP/Pool/Member Inventory 필요
3 | WEB | WEB Node | VM/Physical | MAIN | PROD | WEB | [OPEN] | [OPEN] | [OPEN] | WEB Zone | 다중화/N+1 | DR WEB | [BASELINE] | Apache Instance와 Host 분리
4 | WAS | Marketing WAS Node | VM | MAIN | PROD | WAS | 16C 또는 32C 후보 | 128G 또는 256G 후보 | [OPEN] | WAS Zone | N+1 | DR WAS | [CANDIDATE] | 정확한 승인 사이징은 Load Test 후
5 | DB | RDW DB Node | DB Appliance/Cluster | MAIN | PROD | RDW | [OPEN] | [OPEN] | [OPEN] | DB/Data Network | Cluster/RAC [OPEN] | DR RDW | [BASELINE] | 노드 수/사양 DB Inventory로 확정
6 | DB | ADW DB Node | DB Appliance/Cluster | MAIN | PROD | ADW | [OPEN] | [OPEN] | [OPEN] | DB/Data Network | Cluster/RAC [OPEN] | DR ADW | [BASELINE] | Heavy analytical workload 분리
7 | Event | Broker Node | VM/Physical | MAIN | PROD | Event Platform | [OPEN] | [OPEN] | [OPEN] | Integration Network | Cluster | DR/Event Recovery [OPEN] | [PROPOSED] | Kafka 등 제품 승인 필요
8 | CDC | CDC Relay Node | VM/Physical | MAIN | PROD | CDC | [OPEN] | [OPEN] | [OPEN] | Data Network | Failover/Checkpoint | DR CDC | [PROPOSED] | Capture/Relay/Apply topology 확정 필요
9 | ETL | ETL/Batch Node | VM/Physical | MAIN | PROD | ETL/Batch | [OPEN] | [OPEN] | [OPEN] | Data Network | Restart/Failover | DR ETL | [BASELINE] | Online 자원과 분리
10 | File | MFT/FOS Node | Appliance/VM | MAIN | PROD | File Transfer | [OPEN] | [OPEN] | [OPEN] | File/DMZ/Internal | HA [OPEN] | DR MFT | [BASELINE] | Landing/Archive Storage 포함
11 | Ops | Monitoring/OM Node | VM/Platform | MAIN | PROD | Operations | [OPEN] | [OPEN] | [OPEN] | Management Network | HA [OPEN] | DR Ops | [OPEN] | pdmg-om 실제 구성 미확인
12 | Storage | Backup/Archive | Storage/Backup Appliance | MAIN/DR | PROD | Backup | [OPEN] | [OPEN] | [OPEN] | Backup Network | Redundant Storage | Offsite/DR | [BASELINE] | Restore Test 필수

## E_Software
E Software Registry
No | Domain | Capability | Software/Product | Version/Config | 적용 Runtime | 적용 HW Role | 상태 | Architecture 역할 | 주요 확인/Gap
1 | Runtime | Java Runtime | JDK / Java | 21 | PDMG WAS/JWT | WAS/JWT Node | [AS-IS] | JVM 실행환경 | PDMG Build/Runtime Reference
2 | Runtime | Application Framework | Spring Boot | 3.5.14 | PDMG Service/JWT | WAS/JWT Node | [AS-IS] | Application Runtime | PDMG Source 기준
3 | WEB | Web Server | Apache HTTP Server | [OPEN] | WEB | WEB Node | [BASELINE] | Reverse Proxy/Static/HTTP Entry | 제품/버전 승인 필요
4 | WAS | Servlet Container | Apache Tomcat | [OPEN] | WAS | WAS Node | [BASELINE] | WAR/JVM Runtime | 제품/버전 승인 필요
5 | Framework | Transaction Control | Spring Transaction / TransactionTemplate | Framework config | PDMG Service | WAS Node | [AS-IS] | Worker TX Boundary | Physical TX owner 검증 필요
6 | Framework | Timeout Control | OnlineTimeoutExecutor | 5000ms, pool 20, queue 100 | PDMG Service | WAS Node | [AS-IS] | Worker isolation/deadline | JDBC cancel 보장 아님
7 | Data Access | Connection Pool | HikariCP | Exact version [OPEN] | Business Runtime | WAS Node | [AS-IS] | DB Connection Pool | Target pool size 별도 승인
8 | Data Access | SQL Mapping | MyBatis | Exact version [OPEN] | Business Runtime | WAS Node | [AS-IS] | DAO→Mapper→SQL | Namespace/SqlId trace 중요
9 | Database | RDBMS | Oracle Database | [OPEN] | RDW/ADW | DB Node | [BASELINE] | Operational/Analytical DB | 버전/Edition/Node 수 OPEN
10 | Event | Event Broker | Kafka / Event Broker | [OPEN] | Event | Broker Node | [PROPOSED] | Async Event | 제품 최종 선정 필요
11 | CDC | CDC Platform | Oracle GoldenGate/CDC 계열 | [OPEN] | CDC | CDC Node | [PROPOSED] | Capture/Relay/Apply | 제품/버전 및 SLA 확정 필요
12 | ETL | ETL Engine | ETL Platform | [OPEN] | ETL | ETL Node | [BASELINE] | Bulk transform/load | 제품명 미확정
13 | File | Managed File Transfer | MFT / FOS | [OPEN] | File | MFT/FOS Node | [BASELINE] | File transfer/landing | 제품명 미확정
14 | Security | Security Framework | Spring Security | [OPEN] | PDMG Service/JWT | WAS/JWT Node | [AS-IS] | SecurityFilterChain/JWT | Business authorization 별도
15 | Security | JWT Issuer | RS256 JWT + JWKS | Current source | pdmg-jwt | JWT Node | [AS-IS] | Token issue/JWKS | Key lifecycle/HA 보완
16 | Security | JWT Verifier | HMAC jwt.secret path | Current source | pdmg-fw | WAS Node | [GAP] | Business-side verification | RS256 issuer와 정합성 GAP
17 | Build | Build Tool | Gradle | Multi-project | DEV/CI | Build Node | [AS-IS] | Build/WAR | PDMG Build Reference
18 | SCM | Source Control | GitLab | [OPEN] | DEV/CI | SCM Node | [BASELINE] | Source/Change History | Version/HA 상세 OPEN
19 | CI | CI Runner | GitLab Runner / Jenkins 후보 | [OPEN] | DEV/TEST | Build Node | [PROPOSED] | Build/Test Delivery | 최종 CI 도구구성 확인 필요
20 | Deploy | Production Change/Deploy | eCAMS 전략 | [OPEN] | PROD/DR | Deploy Node | [PROPOSED] | Production deployment/change control | 구현 상세 OPEN
21 | Observability | Monitoring/APM | Monitoring/APM Platform | [OPEN] | All Runtime | Monitoring Node | [BASELINE] | Metric/Trace/Dashboard | 제품/수집범위 OPEN
22 | Logging | Central Logging | Logging Platform | [OPEN] | All Runtime | Monitoring/Storage | [BASELINE] | GUID/ServiceId correlation | 민감정보 Mask 필요
23 | Backup | Backup Software | Backup Platform | [OPEN] | DB/File/Config | Backup Node | [BASELINE] | Backup/Restore | Restore evidence 필요

## F_Interface
F Interface Registry
InterfaceId | Source | Target | Purpose | Protocol/Type | Mode | Status | Evidence | Gap/Next
IF-PD-001 | Browser/UI | PDMG Runtime | Online Business | HTTP/JSON | SYNC | [AS-IS] | Strong current evidence | Endpoint/contract 전수 Registry 필요
IF-PD-002 | PDMG Runtime | RDW / DB | Data Access | MyBatis/JDBC/SQL | SYNC | [AS-IS] | Strong current evidence | Datasource/DB node mapping 필요
IF-PD-003 | Browser/SSO Caller | pdmg-jwt | Login/SSO Token | HTTP(S)/JSON | SYNC | [AS-IS] | JWT source/runtime reference | Exact deployment endpoint inventory 필요
IF-PD-004 | pdmg-jwt | Client | Access/Refresh Token Response | JSON | SYNC | [AS-IS] | Token issue flow | Client token storage risk 검토
IF-PD-005 | Business Runtime | JWT Public Key/JWKS | Token Verification | JWKS/HTTPS | SYNC | [GAP/TARGET] | RS256+JWKS target | Current fw HMAC verifier와 정합 필요
IF-NS-001 | Producer | Event Platform | Business Event | Event/Kafka | ASYNC | [TARGET] | NSIGHT interface policy | Product/topic/schema registry OPEN
IF-NS-002 | Source DB | CDC Consumer/Target | Change Data | CDC | ASYNC | [TARGET/BASELINE] | NSIGHT data movement | Freshness 3s vs 30s conflict
IF-NS-003 | RDW/Source | ADW | Bulk Transform/Load | ETL | ASYNC | [BASELINE] | RDW→ADW role separation | ETL product/job inventory OPEN
IF-NS-004 | Sender | Receiver | Managed File Transfer | MFT/FOS | ASYNC | [BASELINE] | File interface policy | External file inventory OPEN
IF-OPEN-001 | PDMG | External Systems | External API/Event/File | TBD | TBD | [OPEN] | Interface inventory incomplete | InterfaceId/Source/Target 전수등록
IF-OPEN-002 | Any System | Other System DB | Direct DB/DML/DB-Link | JDBC/DB-Link | N/A | [FORBIDDEN/EXCEPTION] | Architecture principle | Privilege/DB-Link exception scan 필요

## G_Config
G Config Registry
Config ID | Key/Item | Value | Source/Runtime | Status | Architecture Meaning | Caution/Gap
CFG-FW-001 | nhnis.fw.tcf.enabled | true | pdmg-fw / application config | [AS-IS] | TCF ON current snapshot | Target policy ≠ snapshot
CFG-FW-002 | nhnis.fw.timeout.enabled | true | pdmg-fw / application config | [AS-IS] | Timeout mechanism enabled
CFG-FW-003 | nhnis.fw.timeout.milliseconds | 5000 | pdmg-fw / application config | [AS-IS] | Worker deadline snapshot | Target SLA 아님
CFG-FW-004 | nhnis.fw.timeout.pool-size | 20 | pdmg-fw / application config | [AS-IS] | PDMG worker pool | Tomcat threads와 별개
CFG-FW-005 | nhnis.fw.timeout.queue-capacity | 100 | pdmg-fw / application config | [AS-IS] | Worker queue | Backpressure capacity
CFG-FW-006 | nhnis.fw.commons.legacy-web.enabled | true | pdmg-fw / application config | [AS-IS] | Legacy web commons enabled | TCF OFF와 동일 의미 아님
CFG-FW-007 | nhnis.fw.commons.filter.enabled | true | pdmg-fw / application config | [AS-IS] | DefaultFilter enabled
CFG-APP-001 | Spring scanBasePackages | nhnis | pdmg-service bootstrap | [AS-IS] | pdmg-service + pdmg-fw same Spring context 가능 | Module ≠ Process
CFG-MYB-001 | Mapper resource pattern | classpath*:rdw.*/*.xml | RdwDataSourceConfig | [AS-IS] | Mapper XML load pattern | Subfolder 구조 변경 주의
CFG-MYB-002 | MapperScan basePackages | nhnis.mg.co.a.persistence.dao | MyBatis config | [AS-IS] | DAO interface scan
CFG-RUN-001 | Java | 21 | Build/Runtime | [AS-IS] | JVM runtime
CFG-RUN-002 | Spring Boot | 3.5.14 | Build/Runtime | [AS-IS] | Application framework
CFG-BLD-001 | Build | Gradle Multi-project | Build config | [AS-IS] | pdmg-service→pdmg-fw, pdmg-jwt→pdmg-fw
CFG-SEC-001 | JWT issuer algorithm | RS256 | pdmg-jwt current source | [AS-IS] | Token issue | Verifier mismatch GAP
CFG-SEC-002 | JWT verifier path | HMAC jwt.secret | pdmg-fw current source | [GAP] | Business-side verification | RS256/JWKS로 정합 필요
CFG-SEC-003 | JWKS exposure | /.well-known/jwks.json pattern | pdmg-jwt current source | [AS-IS] | Public key distribution | Business verifier integration GAP
CFG-TCF-001 | Controller mappings | /online ; /{businessCode}/online ; /{serviceId} | OnlineTransactionController | [AS-IS] | TCF entry mappings | ServiceId mismatch 방어 필요
CFG-TCF-002 | ServiceId resolution | Context header → request header → path variable | Controller runtime | [AS-IS] | Routing key resolution | Mismatch reject currently not confirmed

## H_ADR
H ADR Registry
ID | Domain | Priority | Decision Task | Architecture PASS 여부 | 현행/PDMG 정합 | 판정근거 | 미해결 / PASS 전환조건 | 관련 Architecture
ADR-TASK-001 | Architecture Governance | P0 | Architecture Baseline / SSOT 운영체계 | PASS | PARTIAL | Architecture Closed Loop와 G00~G80/HG90 Baseline/SSOT 체계를 이미 정의함. | Registry/Rule/Runtime Evidence 자동화와 실제 승인 Baseline 운영 필요 | 01 VISION / 07 CLOSED LOOP / 10 INTEGRATED BASELINE
ADR-TASK-002 | Architecture Governance | P0 | Application/Naming/ServiceId Code Registry SSOT | PASS | PARTIAL | Naming·Application Code 표준에서 중앙 Registry와 CI 검증을 SSOT 방향으로 정의함. | ServiceId/InterfaceId/Code Registry 실제 구축 및 UI↔Backend 자동정합 적용 | 별첨 F NAMING / Application Code 정의서
ADR-TASK-003 | Architecture Governance | P0 | PDMG AS-IS ↔ NSIGHT Target Mapping | PASS | PARTIAL | NSIGHT=Target, PDMG=AS-IS Reference로 분리하고 Mapping/ADR을 통해 선택 승격하도록 정의함. | PDMG mg 계열과 NSIGHT MP/업무코드의 전수 Mapping Registry 작성 | 01 VISION / 별첨 A,F
ADR-TASK-004 | Application | P0 | Business Core 진입점 표준 | CONDITIONAL PASS | GAP | Target은 Handler와 Controller가 동일 Business Facade/Core를 공유하는 구조로 정리됨. | TCF OFF Controller→Service 직접호출을 Facade 중심으로 정합시키고 Architecture Test 확보 | 별첨 A APPLICATION
ADR-TASK-005 | Application | P0 | TCF 적용 정책 | CONDITIONAL PASS | PARTIAL | TCF ON 표준 Runtime과 OFF 예외경로를 구분했고 ON 중심 통제구조가 정의됨. | 신규 Online의 TCF ON 기본정책을 ADR로 승인하고 OFF 예외목록/성능근거 확정 | 별첨 A / 06 RUNTIME / 11 DEV STANDARD
ADR-TASK-006 | Application | P1 | Rule Layer 도입범위 | PASS | PARTIAL | Rule Layer는 복잡·재사용 규칙에 선택 적용하는 구조가 Architecture 정의와 정합함. | Rule 적용 기준과 Naming/Package 규칙을 개발표준에 최종 반영 | 별첨 A / 별첨 F
ADR-TASK-007 | Application | P0 | 표준 메시지/헤더 구조 | CONDITIONAL PASS | PARTIAL | hdr_nhnis + dto/result 표준 메시지와 Header/GUID 책임을 정의함. | Filter 조기오류/Resolver 모호성 포함 전 Runtime 경로의 동일 Envelope 보장 및 Contract Test | 06 MESSAGE/CONTEXT/ERROR / 별첨 D
ADR-TASK-008 | Application | P0 | Error Handling / Error Code 표준 | CONDITIONAL PASS | GAP | 중앙 Error Taxonomy/표준 Error Contract 방향은 정의되었으나 현행 Generic/Filter 오류 경로 GAP가 존재함. | Global/Filter 오류 통합, exceptionCode Catalog 연계, 공통 Error Envelope 증적 | 06 MESSAGE/ERROR / 별첨 D
ADR-TASK-009 | Application | P0 | ServiceContext Worker 전달 방식 | PASS | GAP | Worker 경계에서 필요한 Context만 Snapshot으로 전달해야 한다는 Target 원칙이 명확함. | Mutable ServiceContext/Servlet 객체 공유 제거 및 동시성 Test | 06 RUNTIME / 별첨 A
ADR-TASK-010 | Security | P0 | JWT 검증 알고리즘 표준 | PASS | GAP | Security Target은 RS256 Issuer + JWKS 기반 검증으로 정합시키는 방향이 명확함. | pdmg-fw HMAC 검증경로 제거/정합 및 End-to-End JWT 검증 Test | Security/JWT 정의 / 별첨 B
ADR-TASK-011 | Security | P0 | JWT Key Management / Rotation | PASS | GAP | 다중 Instance/DR에서 Versioned Key·kid·JWKS·공유 Key Source가 필요하다고 정의함. | Managed Key Store, Rotation, DR Sync, same-kid same-key 검증 | Security/JWT 정의 / 별첨 B,C
ADR-TASK-012 | Security | P0 | Session / Token State 전략 | CONDITIONAL PASS | OPEN | JWT 중심 + Refresh/Revoke State, HttpSession 최소화 방향은 정해졌으나 Session 60/90분 및 복제방식 Conflict가 남음. | Session TTL/필요범위/Sticky·Replication·Shared Store 중 최종정책 ADR | Security/JWT / 별첨 B,C
ADR-TASK-013 | Security | P0 | Identity Binding / 업무사용자 신뢰체계 | CONDITIONAL PASS | GAP | Trusted Principal을 Header 사용자값보다 우선하는 보안 원칙은 명확하나 현행 Binding GAP가 존재함. | JWT Subject→Business User Context Binding과 Header mismatch 차단 Test | Security/JWT / 06 CONTEXT
ADR-TASK-014 | Interface | P0 | Interface Type Selection 정책 | PASS | PARTIAL | Transaction→API/MCA, Event→Kafka, Change→CDC, Bulk→ETL, File→MFT/FOS로 Purpose-driven 선택을 정의함. | 전 Interface Catalog에 Type 분류 적용 및 예외 ADR | 05 MECHANISM / 별첨 D
ADR-TASK-015 | Interface | P0 | Cross-System Direct DB / DB-Link 정책 | PASS | OPEN | Cross-System Direct DML/DB-Link 금지, Approved Interface/Data Contract 사용 원칙을 명시함. | 현행 Direct DB/DB-Link 전수 Inventory와 예외 승인 정리 | 03 LOGICAL / 별첨 D,E
ADR-TASK-016 | Interface | P1 | SYNC / ASYNC 기본정책 | PASS | OPEN | 현재 거래 완료에 Target 결과가 필수인 경우만 SYNC, 그 외 ASYNC 우선이라는 원칙과 정합함. | 주요 Interface별 Sync/Async 분류와 Failure/Consistency 검증 | 별첨 D INTERFACE
ADR-TASK-017 | Interface | P0 | Timeout Budget 표준 | CONDITIONAL PASS | OPEN | DB Query < Worker/TX < Server/Downstream < Client의 Timeout Hierarchy는 정의됨. | 서비스별 실제 Timeout 값·측정구간·DB Query Timeout을 승인하고 테스트 | 05/06 RUNTIME / 별첨 D
ADR-TASK-018 | Interface | P0 | Retry / Idempotency 정책 | PASS | OPEN | Retryable Error + Backoff + Max Retry + Idempotency/Compensation 정책이 명확히 정의됨. | 거래별 Retry Matrix와 Idempotency Key/보상·DLQ 정책 전수화 | 05 MECHANISM / 별첨 D
ADR-TASK-019 | Interface | P1 | Event Platform 표준 | CONDITIONAL PASS | OPEN | Event Broker/Kafka 기반 비동기 Event 구조는 Target으로 정의되나 제품/버전/Cluster는 미결정. | 표준 Event 제품/Cluster/Schema Registry/운영모델 PoC 및 ADR | 02 BIG PICTURE / 05 MECHANISM / 별첨 D
ADR-TASK-020 | Interface | P1 | 대량/파일 연계 표준 | PASS | PARTIAL | Bulk=ETL, File=MFT/FOS, Online=소량 Transaction 분리 원칙이 정의됨. | 파일/대량 Interface Catalog와 Volume/Reconciliation Test 확보 | 05 MECHANISM / 별첨 D
ADR-TASK-021 | Data | P0 | RDW / ADW 역할분리 | PASS | PARTIAL | RDW=운영·준실시간, ADW=분석·집계·마트의 역할분리가 Baseline으로 명확함. | 실제 DB/Workload/권한/ETL 배치를 Inventory와 성능시험으로 검증 | 별첨 E DATA / 04 PHYSICAL
ADR-TASK-022 | Data | P0 | CDC Freshness SLA | CONDITIONAL PASS | CONFLICT | CDC 경로와 Freshness 측정개념은 정의되었지만 3초 vs 30초 SLA 충돌이 공식적으로 남아 있음. | Source Commit→Consumer Visible 측정점 고정 후 Tier/SLA ADR 승인 | 별첨 E / 별첨 D / 06 RUNTIME
ADR-TASK-023 | Data | P0 | Data Subject / Ownership SSOT | CONDITIONAL PASS | PARTIAL | Data Subject Registry와 Owner/Steward/SOR 구조는 정의됨. | Subject별 Owner/Steward/SOR/Consumer 전수 지정과 Registry 승인 | 별첨 E DATA
ADR-TASK-024 | Data | P1 | Metadata / Lineage / Data Quality 운영방식 | CONDITIONAL PASS | OPEN | Metadata/Lineage/DQ를 Architecture 핵심영역으로 정의했으나 자동수집 도구/범위가 미확정. | Critical Data 우선 자동수집 PoC, DQ Rule Coverage/Repository 운영방식 결정 | 별첨 E DATA
ADR-TASK-025 | Data | P1 | Heavy Analytical Query 격리 | PASS | PARTIAL | Heavy Analytical Query는 ADW로 격리하고 RDW Operational SLA를 보호하도록 정의함. | Query Workload Profile과 Resource Test로 예외/한계치 확정 | 별첨 E / 04 PHYSICAL
ADR-TASK-026 | Infrastructure | P0 | WAS Compute Sizing / Scale-out 단위 | CONDITIONAL PASS | CANDIDATE | Scale-out/Failure Domain 원칙상 중형 VM 다수 구성이 우세하지만 현재 값은 Capacity Candidate임. | 16C/128G vs 32C/256G Load/Soak/N+1/License 비교 후 승인 | 별첨 B,C / HW-SW Matrix
ADR-TASK-027 | Infrastructure | P0 | WEB/WAS 표준 접속 Topology | PASS | PARTIAL | 표준 Working Path를 GSLB→L4→Apache→Tomcat→WAR로 명시함. | 실제 VIP/Apache/Tomcat Topology와 성능·보안 Evidence 확보 | 04 PHYSICAL / 별첨 B,C
ADR-TASK-028 | Infrastructure | P0 | JVM / WAR 배치 및 업무그룹 격리 | PASS | OPEN | 업무그룹별 JVM/WAR 자원·장애격리 원칙과 Server≠JVM≠WAR를 명확히 정의함. | 17 WAR의 그룹 A/B 실제 배치표와 JVM별 Load/Heap/배포영향 검증 | 04 PHYSICAL / 별첨 C
ADR-TASK-029 | Runtime | P0 | Thread / Worker / Hikari Capacity 정책 | CONDITIONAL PASS | OPEN | Tomcat→Worker→Hikari→DB End-to-End Capacity Budget과 Backpressure 원칙은 정의됨. | maxThreads/Hikari/Heap/Worker 승인값을 Load/Stress/Soak 결과로 확정 | 06 RUNTIME / 별첨 B,C / HW-SW Matrix
ADR-TASK-030 | Infrastructure | P0 | 주센터 HA Pattern | PASS | OPEN | WEB/WAS Stateless 계층 Active-Active/N+1, Stateful 기술은 제품특성별 HA라는 구조가 정의됨. | Node Failure/N+1/Session/Key/DB HA 실제 Failure Test | 04 PHYSICAL / 06 RUNTIME / 별첨 C
ADR-TASK-031 | Infrastructure | P0 | DR 운영모델 | CONDITIONAL PASS | OPEN | DR은 Traffic+Artifact+Config+Key+Data+Interface+Monitoring까지 포함하는 구조로 정의됨. | 서비스 Criticality별 Hot/Warm/Cold Tier 및 RTO/RPO, DR Drill 승인 | 06 RUNTIME / 별첨 B,C
ADR-TASK-032 | Data/Infrastructure | P0 | DB HA / DR 구조 | CONDITIONAL PASS | OPEN | RDW/ADW Local HA와 Center DR을 분리하는 원칙은 명확하나 실제 Node/Replication 방식은 미확정. | DB Node 수/제품/Replication/RTO-RPO/Failover-Restore Test 확정 | 04 PHYSICAL / 별첨 C,E
ADR-TASK-033 | DevOps | P1 | CI/CD Orchestration 도구 | OPEN | OPEN | GitLab/Gradle 기반은 확인되지만 GitLab Runner 중심 vs Jenkins 중심의 최종 Orchestration 선택은 Architecture에서 확정하지 않음. | 기존 Jenkins 자산/플러그인/운영역량 조사 후 CI Orchestrator ADR | 09 DEVOPS / 11 DEV STANDARD
ADR-TASK-034 | DevOps | P0 | Artifact Promotion / Deployment Trace | PASS | PARTIAL | sourceCommit→buildId→artifactHash→deploymentId의 Immutable Promotion/Trace 체계를 Baseline으로 정의함. | Artifact Repository/Promotion Pipeline과 Hash 검증 운영 Evidence | 07 CLOSED LOOP / 09 DEVOPS / 10 BASELINE
ADR-TASK-035 | Operations | P0 | Observability 표준 | PASS | PARTIAL | Metric+Structured Log+Trace, ServiceId/GUID/DeploymentId 연계 Observability가 명확히 정의됨. | 실제 APM/Logging 제품, Coverage, Alert/Runbook, Runtime Evidence 연결 | 09 OM/DEVOPS/OBSERVABILITY
ADR-TASK-036 | Operations | P1 | OM Control Plane 구조 | CONDITIONAL PASS | UNKNOWN | OM을 Business Runtime과 분리된 Control Plane으로 보는 Architecture 원칙은 정의됨. | pdmg-om 실제 Source/Runtime Scope 확인 후 Target OM 기능/HA/권한 ADR | 09 OM / 별첨 B
ADR-TASK-037 | Security/DevOps | P0 | Configuration / Secret Management | PASS | OPEN | 환경별 Config 외부화, Secret/Key 분리·보호·DR 동기화 원칙이 Technical/Security Architecture와 정합함. | Secret Store/Config Delivery 제품과 Rotation/Drift Test 확정 | 별첨 B,C / Security Architecture
ADR-TASK-038 | Operations | P0 | Backup / Restore 운영기준 | PASS | PARTIAL | Backup 성공과 Restore/Business Recovery를 분리하고 Restore Test를 필수로 정의함. | 정기 Restore Drill/정합성 검증/증적 보관 프로세스 운영 | 별첨 C,E / 06 RUNTIME
ADR-TASK-039 | DevOps/Operations | P0 | Production Change / Release 통제 | PASS | PARTIAL | Release Manifest·Artifact Hash·DeploymentId·Rollback/Verify 기반의 변경통제 방향이 정의됨. | 생산 배포도구/eCAMS 연계와 승인/자동 Rollback/DR Promotion 운영 검증 | 09 DEVOPS / 10 BASELINE
ADR-TASK-040 | Architecture Governance | P0 | Runtime Evidence 자동수집 / Baseline Release Gate | PASS | PARTIAL | 문서→모델→코드→테스트→Runtime Evidence→Drift→ADR→HG90 Closed Loop가 최상위 원칙으로 확정됨. | Critical Rule의 Evidence Collector/자동 Gate 구현과 G50~HG90 운영 | 01 VISION / 07 CLOSED LOOP / 10 BASELINE

## I_GAP
I GAP Registry
GAP ID | GAP | Severity | Closure / Next | Source
GAP-APP-01 | OFF Controller 5개 Service Direct | High | Facade 정렬 | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md
GAP-APP-02 | Rule Layer 전수 AS-IS 아님 | Medium | 선택기준 ADR | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md
GAP-APP-03 | UI Catalog ↔ 13 Handler Registry | High | 자동비교 | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md
GAP-APP-04 | Dispatcher ID ↔ Context ID mismatch defense | High | Framework 보완 | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md
GAP-APP-05 | 모든 Program Class Stem 전수검증 | Medium | Scanner | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md
GAP-APP-06 | pdmg-om Source/Runtime | Medium/High | Scope 확보 | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md
GAP-APP-07 | Module→Artifact→Process Mapping | High | 05/14장 | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md
GAP-APP-08 | Controller 업무선후처리 가능성 | High | 책임정리 | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md
GAP-APP-09 | TCF OFF 공통 정책 적용 차이 | High | 08/09장 | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md
GAP-APP-10 | Architecture Tests CI 적용 | High | 14/17장 | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md
GAP-CAP-01 | Session 60 vs 90 conflict | High | policy ADR | 16_PDMG_CAPACITY_PERFORMANCE_HA_DR_상세정의서_v1.md
GAP-CAP-02 | Final VM/server count | High | load/cost test | 16_PDMG_CAPACITY_PERFORMANCE_HA_DR_상세정의서_v1.md
GAP-CAP-03 | Tomcat maxThreads approval | High | load/soak | 16_PDMG_CAPACITY_PERFORMANCE_HA_DR_상세정의서_v1.md
GAP-CAP-04 | Hikari target size | High | DB session/capacity test | 16_PDMG_CAPACITY_PERFORMANCE_HA_DR_상세정의서_v1.md
GAP-CAP-05 | JVM heap approval | High | GC/soak | 16_PDMG_CAPACITY_PERFORMANCE_HA_DR_상세정의서_v1.md
GAP-CAP-06 | RTO/RPO | Critical | business approval | 16_PDMG_CAPACITY_PERFORMANCE_HA_DR_상세정의서_v1.md
GAP-CAP-07 | DR drill evidence | Critical | drill | 16_PDMG_CAPACITY_PERFORMANCE_HA_DR_상세정의서_v1.md
GAP-CAP-08 | Session HA final pattern | High | failover test | 16_PDMG_CAPACITY_PERFORMANCE_HA_DR_상세정의서_v1.md
GAP-DA-01 | 실제 Table/View 전수 Inventory 미완료 | High | Mapper/SQL scan | 07_PDMG_DATA_상세정의서_v1.md
GAP-DA-02 | RDW/ADW Datasource 사용현황 미확정 | High | Config/Mapper inventory | 07_PDMG_DATA_상세정의서_v1.md
GAP-DA-03 | Data Owner/Steward/SOR 전수 미확정 | High | Data Registry | 07_PDMG_DATA_상세정의서_v1.md
GAP-DA-04 | Lineage 자동화 미완료 | High | Metadata scanner | 07_PDMG_DATA_상세정의서_v1.md
GAP-DA-05 | DQ Rule/Runtime evidence 미완료 | Medium/High | DQ catalog/test | 07_PDMG_DATA_상세정의서_v1.md
GAP-FW-01 | ServiceId mismatch rejection 미확정 | High | Controller/Dispatcher validation | 08_PDMG_FRAMEWORK_MECHANISM_상세정의서_v1.md
GAP-FW-02 | Mutable ServiceContext worker 공유 | High | Immutable snapshot | 08_PDMG_FRAMEWORK_MECHANISM_상세정의서_v1.md
GAP-FW-03 | Filter/Security early error envelope | High | Common error filter | 08_PDMG_FRAMEWORK_MECHANISM_상세정의서_v1.md
GAP-FW-04 | TCF OFF timeout/control 차이 | High | Policy/adapter alignment | 08_PDMG_FRAMEWORK_MECHANISM_상세정의서_v1.md
GAP-FW-05 | STF/ETF current runtime 미연결 | Medium | Scope/ADR | 08_PDMG_FRAMEWORK_MECHANISM_상세정의서_v1.md
GAP-FW-06 | Generic exception fallback/Advice order | High | Exception test | 08_PDMG_FRAMEWORK_MECHANISM_상세정의서_v1.md
GAP-IF-01 | PDMG External Interface Inventory 미완료 | High | InterfaceId/Source/Target 전수등록 | 06_PDMG_INTERFACE_상세정의서_v1.md
GAP-IF-02 | InterfaceId 정확한 Enterprise 형식 미확정 | Medium | Naming ADR | 06_PDMG_INTERFACE_상세정의서_v1.md
GAP-IF-03 | Timeout/Retry 실제 값 전수 미확정 | High | Contract Registry | 06_PDMG_INTERFACE_상세정의서_v1.md
GAP-IF-04 | CDC SLA 3s vs 30s 충돌 | High | Tiered SLA ADR | 06_PDMG_INTERFACE_상세정의서_v1.md
GAP-IF-05 | Direct DB/DB-Link 예외 Inventory 미완료 | High | Privilege/Link Scan | 06_PDMG_INTERFACE_상세정의서_v1.md
GAP-IF-06 | Replay/Reconciliation Evidence 미완료 | High | Ops test | 06_PDMG_INTERFACE_상세정의서_v1.md
GAP-LT-01 | Access/Web Logical Role 실제 PDMG 배치 정합 | High | 05 | 04_PDMG_LOGICAL_TECHNICAL_ARCHITECTURE_상세정의서_v1.md
GAP-LT-02 | JWT Key/Verifier Runtime 정합 | Critical | 11 | 04_PDMG_LOGICAL_TECHNICAL_ARCHITECTURE_상세정의서_v1.md
GAP-LT-03 | RDW/ADW 실제 Datasource Mapping | High | 07 | 04_PDMG_LOGICAL_TECHNICAL_ARCHITECTURE_상세정의서_v1.md
GAP-LT-04 | External Integration Node/Inventory | High | 06 | 04_PDMG_LOGICAL_TECHNICAL_ARCHITECTURE_상세정의서_v1.md
GAP-LT-05 | OM Logical Node Current Detail | High | 14 | 04_PDMG_LOGICAL_TECHNICAL_ARCHITECTURE_상세정의서_v1.md
GAP-LT-06 | Observability Deployment Correlation | High | 14/17 | 04_PDMG_LOGICAL_TECHNICAL_ARCHITECTURE_상세정의서_v1.md
GAP-LT-07 | Logical Node→Physical Mapping | Critical | 05 | 04_PDMG_LOGICAL_TECHNICAL_ARCHITECTURE_상세정의서_v1.md
GAP-LT-08 | Logical Node State/Scale/HA 속성 실증 | High | 16 | 04_PDMG_LOGICAL_TECHNICAL_ARCHITECTURE_상세정의서_v1.md
GAP-LT-09 | Environment별 Node Inventory | Medium/High | 05 | 04_PDMG_LOGICAL_TECHNICAL_ARCHITECTURE_상세정의서_v1.md
GAP-LT-10 | Product/Version Inventory 정합 | Medium | 05/TRM | 04_PDMG_LOGICAL_TECHNICAL_ARCHITECTURE_상세정의서_v1.md
GAP-MSG-01 | Worker mutable context sharing | High | immutable snapshot | 12_PDMG_MESSAGE_CONTEXT_ERROR_LOGGING_상세정의서_v1.md
GAP-MSG-02 | Filter/Security standard error envelope | High | common error handler | 12_PDMG_MESSAGE_CONTEXT_ERROR_LOGGING_상세정의서_v1.md
GAP-MSG-03 | ServiceId mismatch rejection | High | validation rule | 12_PDMG_MESSAGE_CONTEXT_ERROR_LOGGING_상세정의서_v1.md
GAP-MSG-04 | Generic exception fallback/order | High | fault test | 12_PDMG_MESSAGE_CONTEXT_ERROR_LOGGING_상세정의서_v1.md
GAP-MSG-05 | ImageLog DDL/response field governance | Medium/High | DB/schema governance | 12_PDMG_MESSAGE_CONTEXT_ERROR_LOGGING_상세정의서_v1.md
GAP-MSG-06 | Deployment/Host evidence tags | High | observability integration | 12_PDMG_MESSAGE_CONTEXT_ERROR_LOGGING_상세정의서_v1.md
GAP-NAM-01 | UI catalog vs backend 13 ServiceIds | High | automated diff | 15_PDMG_NAMING_CODE_DEVELOPMENT_STANDARD_상세정의서_v1.md
GAP-NAM-02 | InterfaceId exact enterprise syntax | Medium | ADR/registry | 15_PDMG_NAMING_CODE_DEVELOPMENT_STANDARD_상세정의서_v1.md
GAP-NAM-03 | Event/File/Batch naming | Medium | platform standard | 15_PDMG_NAMING_CODE_DEVELOPMENT_STANDARD_상세정의서_v1.md
GAP-NAM-04 | Artifact/DeploymentId exact syntax | High | DevOps standard | 15_PDMG_NAMING_CODE_DEVELOPMENT_STANDARD_상세정의서_v1.md
GAP-NAM-05 | Hostname/JVM convention | Medium | Infra standard | 15_PDMG_NAMING_CODE_DEVELOPMENT_STANDARD_상세정의서_v1.md
GAP-NAM-06 | Naming scanner CI enforcement | High | pipeline gate | 15_PDMG_NAMING_CODE_DEVELOPMENT_STANDARD_상세정의서_v1.md
GAP-NON-01 | PDMG Event current scope | High | source/inventory scan | 13_PDMG_EVENT_CDC_ETL_BATCH_FILE_CACHE_상세정의서_v1.md
GAP-NON-02 | PDMG Batch current scope | High | job inventory | 13_PDMG_EVENT_CDC_ETL_BATCH_FILE_CACHE_상세정의서_v1.md
GAP-NON-03 | PDMG File current scope | Medium/High | interface inventory | 13_PDMG_EVENT_CDC_ETL_BATCH_FILE_CACHE_상세정의서_v1.md
GAP-NON-04 | Cache current scope/policy | Medium | source/config scan | 13_PDMG_EVENT_CDC_ETL_BATCH_FILE_CACHE_상세정의서_v1.md
GAP-NON-05 | CDC SLA conflict | High | ADR/SLA tier | 13_PDMG_EVENT_CDC_ETL_BATCH_FILE_CACHE_상세정의서_v1.md
GAP-NON-06 | Replay/Reconcile evidence | High | recovery tests | 13_PDMG_EVENT_CDC_ETL_BATCH_FILE_CACHE_상세정의서_v1.md
GAP-OPS-01 | 실제 CI pipeline inventory | High | repository/pipeline scan | 14_PDMG_DEVOPS_OM_OBSERVABILITY_상세정의서_v1.md
GAP-OPS-02 | eCAMS production job current evidence | Medium/High | deployment inventory | 14_PDMG_DEVOPS_OM_OBSERVABILITY_상세정의서_v1.md
GAP-OPS-03 | pdmg-om current implementation | High | source/runtime evidence | 14_PDMG_DEVOPS_OM_OBSERVABILITY_상세정의서_v1.md
GAP-OPS-04 | Artifact→Host/JVM/WAR trace | Critical | deployment manifest | 14_PDMG_DEVOPS_OM_OBSERVABILITY_상세정의서_v1.md
GAP-OPS-05 | metric/log/trace integrated correlation | High | observability implementation | 14_PDMG_DEVOPS_OM_OBSERVABILITY_상세정의서_v1.md
GAP-OPS-06 | restore/DR evidence | High | drill | 14_PDMG_DEVOPS_OM_OBSERVABILITY_상세정의서_v1.md
GAP-PHY-01 | PDMG Artifact→Host/JVM/WAR 실배치 미완료 | Critical | Deployment/CMDB Mapping | 05_PDMG_PHYSICAL_INFRASTRUCTURE_상세정의서_v1.md
GAP-PHY-02 | 실제 Host/VM/Port Inventory 미확보 | High | Infra Inventory | 05_PDMG_PHYSICAL_INFRASTRUCTURE_상세정의서_v1.md
GAP-PHY-03 | JVM/WAR 업무그룹 승인안 미확정 | High | Load/Failure Test + ADR | 05_PDMG_PHYSICAL_INFRASTRUCTURE_상세정의서_v1.md
GAP-PHY-04 | RTO/RPO 미확정 | High | Business DR Tier | 05_PDMG_PHYSICAL_INFRASTRUCTURE_상세정의서_v1.md
GAP-PHY-05 | DB HA/DR 제품/노드 상세 미확정 | High | DB Inventory/Test | 05_PDMG_PHYSICAL_INFRASTRUCTURE_상세정의서_v1.md
GAP-PHY-06 | Backup Restore Evidence 미확보 | High | Restore Drill | 05_PDMG_PHYSICAL_INFRASTRUCTURE_상세정의서_v1.md
GAP-RT-01 | Worker context mutable sharing | High | immutable snapshot | 09_PDMG_ONLINE_RUNTIME_상세정의서_v1.md
GAP-RT-02 | JWT identity binding | Critical | principal binding | 09_PDMG_ONLINE_RUNTIME_상세정의서_v1.md
GAP-RT-03 | TCF OFF facade parity | High | controller→facade | 09_PDMG_ONLINE_RUNTIME_상세정의서_v1.md
GAP-RT-04 | generic/early error coverage | High | fault tests | 09_PDMG_ONLINE_RUNTIME_상세정의서_v1.md
GAP-RT-05 | JDBC cancel/query timeout evidence | High | driver/query test | 09_PDMG_ONLINE_RUNTIME_상세정의서_v1.md
GAP-RT-06 | Runtime→deployment correlation | High | deploymentId/host/jvm tags | 09_PDMG_ONLINE_RUNTIME_상세정의서_v1.md
GAP-SEC-01 | RS256 issuer vs HMAC verifier | Critical | RS256/JWKS integration | 11_PDMG_SECURITY_SSO_JWT_SESSION_상세정의서_v1.md
GAP-SEC-02 | Key lifecycle/multi-instance consistency | Critical | managed key store/rotation | 11_PDMG_SECURITY_SSO_JWT_SESSION_상세정의서_v1.md
GAP-SEC-03 | Denylist verifier integration | High | revocation test | 11_PDMG_SECURITY_SSO_JWT_SESSION_상세정의서_v1.md
GAP-SEC-04 | Principal↔Business user binding | Critical | binding enforcement | 11_PDMG_SECURITY_SSO_JWT_SESSION_상세정의서_v1.md
GAP-SEC-05 | ServiceId authorization matrix | High | authz registry | 11_PDMG_SECURITY_SSO_JWT_SESSION_상세정의서_v1.md
GAP-SEC-06 | sessionStorage token exposure risk | High | client security review | 11_PDMG_SECURITY_SSO_JWT_SESSION_상세정의서_v1.md
GAP-TR-01 | Architecture model automation completeness | High | entity/relation registry | 17_PDMG_TRACEABILITY_PASS_GAP_ADR_상세정의서_v1.md
GAP-TR-02 | Source scanner CI enforcement | High | pipeline | 17_PDMG_TRACEABILITY_PASS_GAP_ADR_상세정의서_v1.md
GAP-TR-03 | Deployment runtime correlation | Critical | deployment manifest | 17_PDMG_TRACEABILITY_PASS_GAP_ADR_상세정의서_v1.md
GAP-TR-04 | Runtime evidence collector | Critical | metrics/trace/test link | 17_PDMG_TRACEABILITY_PASS_GAP_ADR_상세정의서_v1.md
GAP-TR-05 | UI/backend registry drift automation | High | catalog diff | 17_PDMG_TRACEABILITY_PASS_GAP_ADR_상세정의서_v1.md
GAP-TR-06 | Critical decision closure | Critical | ADR/gate | 17_PDMG_TRACEABILITY_PASS_GAP_ADR_상세정의서_v1.md
GAP-TX-01 | DB/JDBC Query Timeout exact value 미확정 | Critical | driver/config test | 10_PDMG_TRANSACTION_TIMEOUT_THREAD_DB_상세정의서_v1.md
GAP-TX-02 | cancel(true) DB cancel guarantee 없음 | High | statement cancel test | 10_PDMG_TRANSACTION_TIMEOUT_THREAD_DB_상세정의서_v1.md
GAP-TX-03 | mutable worker context | High | immutable snapshot | 10_PDMG_TRANSACTION_TIMEOUT_THREAD_DB_상세정의서_v1.md
GAP-TX-04 | Hikari target size 미확정 | High | load/DB test | 10_PDMG_TRANSACTION_TIMEOUT_THREAD_DB_상세정의서_v1.md
GAP-TX-05 | Tomcat/worker/pool capacity evidence 미완료 | High | load/soak | 10_PDMG_TRANSACTION_TIMEOUT_THREAD_DB_상세정의서_v1.md
GAP-TX-06 | late worker runtime evidence 미완료 | High | timeout fault test | 10_PDMG_TRANSACTION_TIMEOUT_THREAD_DB_상세정의서_v1.md

## J_Evidence
J Evidence Registry
Evidence ID | Type | Artifact / Evidence | Supports | Status | Domain
EVD-001 | Source/Architecture | 03_PDMG_APPLICATION_MODULE_ARCHITECTURE_상세정의서_v1.md | Module/Package/Handler Registry/TCF ON-OFF | [AS-IS REFERENCE] | Application
EVD-002 | Source/Runtime | NSIGHT_PDMG_아키텍처_정의서_08_PDMG_SOURCE_RUNTIME_REFERENCE_DEEP_DIVE_VISUAL_FIRST_상세본_보완개정본_v2.md | Source Tree/Runtime/Mapper/Controller Drift | [AS-IS REFERENCE] | Application/Runtime
EVD-003 | Runtime | NSIGHT_PDMG_아키텍처_정의서_IV_PDMG_Online_Runtime_TCF_Flow.md | TCF Online Runtime Flow | [AS-IS REFERENCE] | Mechanism/Runtime
EVD-004 | Runtime | NSIGHT_PDMG_아키텍처_정의서_V_Transaction_Timeout_Thread_DB_Architecture.md | Thread/Timeout/Transaction/DB | [AS-IS REFERENCE] | Runtime/Capacity
EVD-005 | Message/Context | NSIGHT_PDMG_아키텍처_정의서_VI_Standard_Message_Context_Error_Logging.md | hdr_nhnis/dto/result, Context, Error, ImageLog | [AS-IS REFERENCE] | Message/Operations
EVD-006 | Security | NSIGHT_PDMG_아키텍처_정의서_VII_Security_SSO_JWT_Session.md | SSO/JWT/Session/Security GAP | [AS-IS REFERENCE] | Security
EVD-007 | Infrastructure | NSIGHT_PDMG_아키텍처_정의서_VIII_Infrastructure_WAS_Capacity_HA_DR.md | WEB/WAS/Capacity/HA/DR | [WORKING REFERENCE] | Physical/HA-DR
EVD-008 | DevOps/Ops | NSIGHT_PDMG_아키텍처_정의서_IX_DevOps_OM_Observability.md | Build/Deploy/OM/Observability | [WORKING REFERENCE] | DevOps/Ops
EVD-009 | Naming/Trace | NSIGHT_PDMG_아키텍처_정의서_X_Naming_ServiceId_Traceability_Closed_Loop.md | Program/ServiceId/Traceability | [AS-IS+TARGET] | Naming/Trace
EVD-010 | Application Code | NSIGHT_PDMG_어플리케이션_코드_정의서_VISUAL_FIRST.md | MP/RD/AD/BI/DG/IM 50 Application codes | [BASELINE] | Application Code
EVD-011 | HW/SW Inventory | NSIGHT_PDMG_하드웨어_소프트웨어_매트릭스.xlsx | HW/SW/Capacity/Status Matrix | [BASELINE/CANDIDATE/OPEN] | Physical/Technical
EVD-012 | Decision | NSIGHT_PDMG_아키텍처_의사결정_레지스터_PASS평가_v2.xlsx | 40 ADR Tasks / PASS-Conformance | [DECISION] | Governance
EVD-013 | Interface | 06_PDMG_INTERFACE_상세정의서_v1.md | HTTP/JDBC current + Interface policy/GAP | [AS-IS+TARGET] | Interface
EVD-014 | Data | 07_PDMG_DATA_상세정의서_v1.md | RDW/ADW/Data ownership/lineage | [BASELINE/PARTIAL] | Data
EVD-015 | Framework | 08_PDMG_FRAMEWORK_MECHANISM_상세정의서_v1.md | Filter/Security/TCF/Timeout/TX/Error | [AS-IS REFERENCE] | Mechanism
EVD-016 | Runtime | 09_PDMG_ONLINE_RUNTIME_상세정의서_v1.md | Request/Worker Runtime/Failure | [AS-IS REFERENCE] | Runtime
EVD-017 | Capacity | 16_PDMG_CAPACITY_PERFORMANCE_HA_DR_상세정의서_v1.md | Capacity candidates/HA/DR | [CANDIDATE/BASELINE] | Capacity
EVD-018 | Traceability | 17_PDMG_TRACEABILITY_PASS_GAP_ADR_상세정의서_v1.md | Gate/GAP/ADR/Closed Loop | [DECISION] | Governance
EVD-019 | Final Definition | NSIGHT_PDMG_ARCHITECTURE_BOOK_FINAL_V5.md | 13-chapter final Architecture Story/Definition | [FINAL EDITION] | All
EVD-020 | Config Snapshot | nhnis.fw.* current config snapshot | TCF true / timeout true / 5000ms / pool20 / queue100 / filter true | [AS-IS] | Framework Runtime
EVD-021 | Runtime Evidence Gap | Deployment/Runtime Evidence Collector | sourceCommit→artifactHash→deploymentId→serviceId→trace | [OPEN] | HG90
EVD-022 | CMDB Gap | Host/VM/JVM/WAR Inventory | Actual production placement | [OPEN] | Physical
EVD-023 | Security Test Gap | JWT End-to-End Integration Test | RS256 issuer↔JWKS verifier / key rotation / DR | [OPEN] | Security
EVD-024 | Timeout Test Gap | JDBC Query Timeout/Cancel/Late Worker Test | HTTP 504 vs Worker/JDBC/DB behavior | [OPEN] | Runtime
EVD-025 | DR Test Gap | Restore/Failover/Failback Business Validation | RTO/RPO and recovery evidence | [OPEN] | HA/DR